## Sheet1
Context: | Software Product Design and Development I
Project: | Fantastic title (*)
DocumentType: | Plan
Version: | 2.1 (*)
Date: | Oct 23, 2022 (*)
Author: | John Businge
Status: | Example (*)
| Total Time Budget (*) | 240
| Total Spent (*) | 226
| Total Estimated (*) | 24.04
| Balance | -10.04 | << overtime ?
TIME
Use-case Id(+) | Use-case (+) | Priority (*) | Delivery (*) | #steps (+) | estimated(+) | spent(+)
DELIVERED 2.0
1.1 | … | REQUIRED | 2022-02-18 | 12 | nil | 53.5
2.1 | … | REQUIRED | 2002-02-18 | 6 | nil | 23
1.2 | … | REQUIRED | 2002-03-22 | 9 | 38.25 | 36
1.4 | … | IMPORTANT | 2002-03-22 | 10 | 42.5 | 40
1.5 | … | IMPORTANT | 2002-03-22 | 10 | 42.5 | 73.5 | << had bad luck
|  |  |  | 47 |  | 226
| sum(Spent) / sum(# Steps) | = 226 / 47 | m = | 4.8085 | << recalculate
TO BE DELIVERED 2.1 |  |  |  | x | y = m * x
2.2 | … | IMPORTANT | 2022-04-27 | 4 | 19.234
1.3 | … | USEFUL | 2022-04-27 | 2 | 9.617
1.6 | … | USEFUL | 2022-04-27 | 3 | 14.4255 | << delete ?
2.3 | … | USEFUL | --not | 2 | 0
2.4 | … | USEFUL | --not | 5 | 0
24.0426
(*)To adjust
(+)Columns to customize