## Sheet1
Context: | Software Product Design and Development I
Project: | Fantastic title (*)
Document Type: | Plan
Version: | 2.0 (*)
Date: | October 23, 2022 (*)
Author: | John Businge
Status: | Example (*)
| Total Time Budget (*) | 240
| Total Spent (*) | 76.5
| Total estimated 2.0(*) | 140.25
| Total estimated 2.1(*) | 51
| Balance | -27.75 | << shortage
TIME
Use-case Id(+) | Use-case (+) | Priority (*) | Delivery (*) | #steps (+) | estimated(+) | spent(+)
DELIVERED 1.0
1.1 | … | REQUIRED | 2022-03-01 | 12 | nil | 53.5
2,1 | … | REQUIRED | 2002-03-01 | 6 | nil | 23
|  |  |  | 18 |  | 76.5
| sum(Spent) / sum(# Steps) | = 76,5 / 18 | m = | 4.25 | << recalculate
OP TE LEVEREN 2.0 |  |  |  | x | y = m * x
1.2 | … | REQUIRED | 2022-03-22 | 9 | 38.25
1.4 | … | IMPORTANT | 2022-03-22 | 10 | 42.5
1.5 | … | IMPORTANT | 2022-03-22 | 10 | 42.5
2.2 | … | IMPORTANT | 2022-03-22 | 4 | 17
140.25
TO BE DELIVERED 2.1 |  |  |  | x | y = m * x
1.3 | … | USEFUL | 2022-04-27 | 2 | 8.5
1.6 | … | USEFUL | 2022-04-27 | 3 | 12.75
2.3 | … | USEFUL | 2022-04-27 | 2 | 8.5 | << delete
2.4 | … | USEFUL | 2022-04-27 | 5 | 21.25 | << delete
51
(*)To adjust
(+)Columns to customize